## Contents
JANU GP1 / MUR — Procurement Tracker
Discipline / Package | Items | Sub-Categories | Sub-Category List
01 Plaster | 4 | 1 | Plaster Finishes
02 Stone | 7 | 1 | Natural Stone
03 Doors | 16 | 2 | Door Hardware & Ironmongery · Wooden Doors (Leaves & Frames)
04 Glazing | 9 | 2 | Glass & Framing · Glazing Hardware & Sliding Gear
05 FF&E | 40 | 3 | Fabrics · Fixtures · Furniture
06 Millwork & Joinery | 9 | 6 | Artwork, Booth & Nightstands · Bed · Cabinet Hardware · Closet Joinery · Headboard · Minibar
07 Plumbing Systems | 1 | 1 | Plumbing Specialties
08 Plumbing Equipment | 5 | 1 | Domestic Water Piping & Valves
09 Pool & Water Features | 34 | 10 | Balancing Tank & Specialties · Filtration · Pool Bonding & Electrical · Pool Controls & Automation · Pool Fittings · Pool Heating · Pool Lighting · Pool Piping & Valves · Pool Pumps · Sanitization & Chlorination
10 Electrical | 14 | 3 | Feeders, Cable, Conduit & Ground · Panelboards & Distribution · Wiring Devices & Power
11 Low Voltage & ICT | 1 | 1 | Telephone, CATV, IT & Data
12 Lighting | 42 | 4 | Architectural Luminaires · Decorative Fixtures · LED Strips & Drivers · Lighting Control System (Lutron)
13 HVAC & Mechanical | 17 | 7 | Air Distribution · Condensing Units · Controls / Thermostats · Ductwork, Dampers & Insulation · Indoor Units (Fan Coils) · Refrigerant Piping · Ventilation / Exhaust Fans
TOTAL | 199

## 01 Plaster
01 Plaster
4 items · filter by Sub-Category to drill in
# | Sub-Category | Code / Tag | Item / Description | Location / Zone | Manufacturer / Brand | Model / SKU | Qty | Unit | Spec Ref | Spec Sheet | Approved | Procured | Notes
1 | Plaster Finishes | PLEX-01 | Plaster Exterior Walls | Exterior Walls |  |  | 1548 | SF
2 | Plaster Finishes | PLEX-02 | Plaster Exterior Ceilings | Exterior Ceilings |  |  | 265 | SF
3 | Plaster Finishes | PLIN-01 | Plaster Interior Ceilings | Interior Ceilings |  |  | 785 | SF
4 | Plaster Finishes | PLIN-02 | Plaster Interior Walls | Interior Walls |  |  | 396 | SF

## 02 Stone
02 Stone
7 items · filter by Sub-Category to drill in
# | Sub-Category | Code / Tag | Item / Description | Location / Zone | Manufacturer / Brand | Model / SKU | Qty | Unit | Spec Ref | Spec Sheet | Approved | Procured | Notes
1 | Natural Stone | Creme du Provence | Creme du Provence — Column 1-7 cladding (40mm) + Bathroom Vanity legs B3, B4 (20mm) | Column 1-7 cladding (40mm) + Bathroom Vanity legs B3, B4 (20mm) |  | Millwork schedule | 80 | pcs
2 | Natural Stone | Mocca Cafe | Mocca Cafe — Bathroom Vanity countertop B1 + cover strips; Nightstands (left and right) | Bathroom Vanity countertop B1 + cover strips; Nightstands (left and right) |  | Millwork schedule | 15 | pcs
3 | Natural Stone | Ocean Black Bricks | Ocean Black Bricks — Entrance platform and steps, entrance inside, bathroom, walk-in closet, bedroom, terrace and step - 12 zones | Entrance platform and steps, entrance inside, bathroom, walk-in closet, bedroom, terrace and step - 12 zones |  | Floor / pool take-off | 3370 | pcs
4 | Natural Stone | Ocean Black Slabs | Ocean Black Slabs — WC and indoor shower pans, small pan, drain covers, threshold strip, rinse showers | WC and indoor shower pans, small pan, drain covers, threshold strip, rinse showers |  | Floor / pool take-off | 10 | pcs
5 | Natural Stone | Red Soraya Travertine | Red Soraya Travertine — Mini Bar Cabinetry; Closets Behind the Bed (20mm, built up to 76mm) | Mini Bar Cabinetry; Closets Behind the Bed (20mm, built up to 76mm) |  | Millwork schedule | 18 | pcs
6 | Natural Stone | Sukabumi Slabs | Sukabumi Slabs — Pool floors and stair steps, deep walls and stair risers, shallow walls, through-basin walls | Pool floors and stair steps, deep walls and stair risers, shallow walls, through-basin walls |  | Floor / pool take-off | 2224 | pcs
7 | Natural Stone | Tundra Beige | Tundra Beige — Outdoor Terrace Bench; Indoor Shower Bench & Towel Hanger (A1-A9); Bathroom Vanity B2; Outdoor Towel Hanger (G1-G5); Day Bed H2/H3; Outdoor Entry Door Bench | Outdoor Terrace Bench; Indoor Shower Bench & Towel Hanger (A1-A9); Bathroom Vanity B2; Outdoor Towel Hanger (G1-G5); Day Bed H2/H3; Outdoor Entry Door Bench |  | Millwork schedule | 77 | pcs

## 03 Doors
03 Doors
16 items · filter by Sub-Category to drill in
# | Sub-Category | Code / Tag | Item / Description | Location / Zone | Manufacturer / Brand | Model / SKU | Qty | Unit | Spec Ref | Spec Sheet | Approved | Procured | Notes
1 | Door Hardware & Ironmongery | 1 ¦ D-01,D-02,D-03 | Concealed door hinge, flush interior doors up to 80/100 kg, brushed copper | W.C., Entrance, Bathroom | Haefele |  | 18 | no | A11-02/03/04 | Not Started
2 | Door Hardware & Ironmongery | 2 ¦ D-01 | Lever handle set; NE-Black Chrome | Doors | Salto | Salto Standard Line / London Model | 3 | set | A11-02/03/04 | Not Started
3 | Door Hardware & Ironmongery | 2.2 ¦ D-03 | Teak Wood Handle | W.I.C | CBMmart | Exterior Grade Teak Wood Planks and Regular Teak Wood Planks | 3 |  | A11-02/03/06
4 | Door Hardware & Ironmongery | 3 ¦ D-01 | Electronic lockset | Entrance | Salto | Salto Element Fusion - ANSI | 1 | no | A11-02 | Not Started
5 | Door Hardware & Ironmongery | 4 ¦ D-04 | Privacy Thumb Turn | W.C. | Salto | Sargent 8200 Series | 1 | no | A11-04 | Not Started
6 | Door Hardware & Ironmongery | 5 ¦ D-01 | Startec door viewer, brushed brass | Entrance | Hafele | Startec 200° 82mm door viewer | 1 | no | A11-02 | Not Started
7 | Door Hardware & Ironmongery | 6 ¦ D-03 | Sliding door running gear (80/100 8-piece system) | Closet | Hafele | Junior 80/B-Pocket | 1 | set | A11-03 | Not Started
8 | Door Hardware & Ironmongery | 6.1 ¦ S-02 | Sliding door running gear (80/100 8-piece system) | Louver | Hafele | Slido D-Line11 160p |  |  | A11-02/03/04
9 | Door Hardware & Ironmongery | 7 ¦ D-01 | Automatic Drop Down Seal | All doors | Assa Abloy | Planet X3, RD | 1 | lot | A11-02/03/04 | Not Started
10 | Door Hardware & Ironmongery | 7.1 ¦ D-02,D-03,D-04 | Sealing rubber frame strips | All doors | Reflect |  | 3 | lot | A11-02/03/04 | Not Started
11 | Wooden Doors (Leaves & Frames) | 1 ¦ S-01 | Bedroom shutter - fixed glass + openable louver + roll blackout | Bedroom |  | Teak hardwood + tempered glass | 1 | no | A11-02 | In Progress |  |  | Finish TBC by MMM. Blackout Lutron R64 = shades (separate scope)
12 | Wooden Doors (Leaves & Frames) | 2 ¦ S-02 | Outside living sliding louver doors | Outdoor living |  | Teak hardwood + tempered glass | 1 | no | A11-02 | In Progress |  |  | Sliding louver on track
13 | Wooden Doors (Leaves & Frames) | 3 ¦ D-01 | Entrance door - fixed + swinging | Entrance |  | Teak hardwood / plywood | 1 | no | A11-02 | In Progress |  |  | 6 concealed hinges
14 | Wooden Doors (Leaves & Frames) | 4 ¦ D-02 | Bathroom door - swinging | Bathroom |  | Teak hardwood / plywood | 1 | no | A11-03 | In Progress
15 | Wooden Doors (Leaves & Frames) | 5 ¦ D-03 | Walk-in closet - sliding louvered doors | Closet |  | Teak hardwood / plywood | 1 | no | A11-03 | In Progress
16 | Wooden Doors (Leaves & Frames) | 6 ¦ D-04 | W.C. door - swinging | W.C. |  | Teak hardwood / plywood | 1 | no | A11-04 | In Progress

## 04 Glazing
04 Glazing
9 items · filter by Sub-Category to drill in
# | Sub-Category | Code / Tag | Item / Description | Location / Zone | Manufacturer / Brand | Model / SKU | Qty | Unit | Spec Ref | Spec Sheet | Approved | Procured | Notes
1 | Glass & Framing | 1 ¦ GL.01 | Sliding glazed door into pocket (19 ft 9 in x 9 ft 3-3/4 in) | Bedroom | Assumed ES Windows | Clear glass; structural aluminium, custom anodized | 1 | no | A12-02 | In Progress
2 | Glass & Framing | 2 ¦ GL.02 | Sliding glazed door into pocket (8 ft 1-1/2 in x 9 ft 3-3/4 in) | Bathroom | Assumed ES Windows | Clear glass; structural aluminium, custom anodized | 1 | no | A12-02 | In Progress
3 | Glass & Framing | 3 ¦ GL.03 | Fixed window (4 ft 1 in x 9 ft 3-3/4 in) | Bedroom/entrance/bath | Assumed ES Windows | Clear glass; structural aluminium, custom anodized | 5 | no | A12-02 | In Progress
4 | Glass & Framing | 4 ¦ GL.04 | Fixed window (1 ft 6 in x 9 ft 3-3/4 in) | Bathroom | Assumed ES Windows | Clear glass; structural aluminium, custom anodized | 2 | no | A12-02 | In Progress
5 | Glass & Framing | 5 ¦ GL.05 | Sliding glazed door into pocket (11 ft 11-1/2 in x 9 ft 3-3/4 in) | Bedroom | Assumed ES Windows | Clear glass; structural aluminium, custom anodized | 1 | no | A12-03 | In Progress
6 | Glass & Framing | 6 ¦ GL.06 | Fixed window (small, bathroom) | Bathroom | Assumed ES Windows | Clear glass; structural aluminium, custom anodized | 1 | no | A12-03 | In Progress
7 | Glass & Framing | 7 ¦ GL.07 | Swinging (hinged) glazed door (2 ft 8 in x 9 ft) | Bathroom | Assumed ES Windows | Clear glass; structural aluminium, custom anodized | 1 | no | A12-03 | In Progress
8 | Glass & Framing | 8 ¦ GL.08 | Swinging (hinged) glazed door (4 ft 1 in x 9 ft 3-3/4 in) | Bathroom | Assumed ES Windows | Clear glass; structural aluminium, custom anodized | 1 | no | A12-03 | In Progress
9 | Glazing Hardware & Sliding Gear | 1 | Double handle with invisible integrated lock | Glazed doors | Ottima |  | 5 | set | A12-02/03 | In Progress

## 05 FF&E
05 FF&E
40 items · filter by Sub-Category to drill in
# | Sub-Category | Code / Tag | Item / Description | Location / Zone | Manufacturer / Brand | Model / SKU | Qty | Unit | Spec Ref | Spec Sheet | Approved | Procured | Notes
1 | Fabrics | CUR-01 | Blackout Curtains Aznar FR Twin Face Blackout 063 | Bedroom | Aznar Textile | FR Twin Face Blackout 063
2 | Fabrics | UPH-01 | Outdoor Fabric Bikaina YP25004 Ausarta Collection | Bedroom | Designs of the Time | Bikaina YP25004 Ausarta Collection
3 | Fabrics | UPH-02 | Outdoor Fabric TULUM col. 12 | Bedroom | Guell la madrid | TULUM col. 12
4 | Fabrics | CUR-02 | Stripe Sheer plum | Bedroom | HOLLAND AND SHERRY | 75360 Osian Collection 97501/CB
5 | Fabrics | RUG-01 | Mioro Outdoor Rug 0225 by Margrethe Odgaard | Bedroom | Kvadrat | Mioro Outdoor
6 | Fabrics | UPH-03 | In-Outdoor Fabric Tan Tan 60482 Col. 13093 | Bedroom | Maria Flora | Tan Tan 60482 Col. 13093
7 | Fabrics | UPH-04 | In-Outdoor Fabric Crisalide 60724 Col. 131 | Outdoor Living / Outdoor terrace (uncovered) | Maria Flora | Crisalide 60724 Col. 131
8 | Fabrics | UPH-05 | In-Outdoor Fabric Zagora | Exterior terrace | Maria Flora | Zagora 60749 Col. 13093
9 | Fabrics | UPH-06 | Outdoor Fabric ACERO 60002 | Outdoor / daybeds | Maria Flora | ACERO 60002 COL. 15102
10 | Fabrics | UPH-07 | In-Outdoor Fabric Camaleonte 60725 Col. 70 | Outdoor Living / Outdoor terrace (uncovered) | Maria Flora | Camaleonte 60725 Col. 70
11 | Fabrics | UPH-08 | In-Outdoor Fabric Rugged Stripe Driftwood | Outdoor terrace / Daybeds | Perennials | Rugged Stripe 895-101 Color:Driftwood
12 | Fabrics | UPH-09 | In-Outdoor Fabric Flanders Dirty Martini | Outdoor terrace / Daybeds | Perennials | Flanders 941-364 Color:Dirty Martini
13 | Fabrics | UPH-10 | Marine contract fabric Blend Linen 16001-0014 Sunbrella Upholdstery Collection | Daybeds Interior | Sunbrella | Blend Linen 16001-0014
14 | Fabrics | UPH-11 | Outdoor fabric | Cushions Tribu KOS chair | TRIBU | E-81
15 | Fixtures | FIX-01 | Deck-mounted basin spout without pop-up waste | Bathroom (Vanity) | Dorn Bracht | Deck mounted 13 716 882-42 | 2
16 | Fixtures | FIX-02 | Deck valve clockwise closing cold | Indoor Shower | Dorn Bracht | Deck Valve 20 000 740-46 | 1
17 | Fixtures | FIX-03 | Hand shower set with integrated shower holder FlowReduce | Rinse Shower & Indoor Shower | Dorn Bracht | Hand shower 27 812 660-42 0010 | 2
18 | Fixtures | FIX-04 | Rain shower with ceiling fixing FlowReduce 400 mm - Brushed Bronze | Rinse Shower & Indoor Shower | Dorn Bracht | Rain shower 28 698 970-42 | 2
19 | Fixtures | FIX-05 | META xTOOL Thermostat module with 1 valve | Rinse Shower & Indoor Shower | Dorn Bracht | Thermostat module 36 503 979-42 + 36 607 740-42 | 3
20 | Fixtures | FIX-06 | Wall mounted clothing hook | Bathroom, Walk-in Closet & Rinse Shower | Dorn Bracht | Hooks 83 251 220-42 | 8
21 | Fixtures | FIX-07 | Tissue holder without cover | Guests & ADA Restroom | Dorn Bracht | Tissue holder 83 500 979-42 | 1
22 | Fixtures | FIX-08 | TOTO Neorest WX1 Wall Hung Toilet | WC | TOTO | Neorest wx1 CWT9538CEMFG#01 | 1
23 | Furniture | CUSH-01 | Decorative cushion | #VALUE! | CUSTOM | CUSTOM MADE | 2
24 | Furniture | CUSH-02 | Decorative cushion | #VALUE! | CUSTOM | SQUARE | 6
25 | Furniture | CUSH-03 | Decorative cushion | #VALUE! | CUSTOM | RECTANGULAR | 2
26 | Furniture | CUSH-04 | Decorative cushion | #VALUE! | CUSTOM | SQUARE | 2
27 | Furniture | CUSH-05 | Decorative cushion | #VALUE! | CUSTOM | RECTANGULAR | 1
28 | Furniture | CUSH-06 | SEAT CUSHION | #VALUE! | CUSTOM | CUSTOM MADE | 1
29 | Furniture | CUSH-07 | Decorative cushion | #VALUE! | CUSTOM | CUSTOM MADE | 1
30 | Furniture | CUSH-11 | SEAT CUSHION | #VALUE! | CUSTOM | CUSTOM MADE | 1
31 | Furniture | FURN-01 | Foot Stool | Bathroom & Walk in Closet | CARL HANSEN & SON (Hans J. Wegner) | CH53 | 1
32 | Furniture | FURN-02 | Dining Chair | Bedroom / Outdoor Terrace | BRDR. KRUGER | ARV chair | 1
33 | Furniture | FURN-04 | "Mesa Recinto" Colección Brutal | Bedroom (Booth) | Habitación 116 | Mesa recinto | 1
34 | Furniture | FURN-05 | "Mesa Recinto 90" Colección Brutal | Outdoor Terrace | Habitación 116 | Mesa recinto 80 | 1
35 | Furniture | FURN-06 | "Tambor" Colección Brutal | Outdoor Terrace | Habitación 116 | Tambor brutal | 1
36 | Furniture | FURN-08 | JANU Lounge Chair | Bedroom | MCE | Custom made | 1
37 | Furniture | FURN-09 | JANU Nightstand | Bedroom | MCE | Custom made | 1 | [5 empty] | Possible overlap with 06 Millwork › Nightstands — verify
38 | Furniture | FURN-10 | Tray | Outdoor Bench / Outdoor Living | MCE | Custom made | 2
39 | Furniture | FURN-07 | JANU Lounge Chair | Outdoor shower | POLIFORM | DAMA | 1
40 | Furniture | FURN-03 | Lounge Chair | Outdoor Terrace | TRIBÚ | KOS lounge chair | 1

## 06 Millwork & Joinery
06 Millwork & Joinery
9 items · filter by Sub-Category to drill in
# | Sub-Category | Code / Tag | Item / Description | Location / Zone | Manufacturer / Brand | Model / SKU | Qty | Unit | Spec Ref | Spec Sheet | Approved | Procured | Notes
1 | Artwork, Booth & Nightstands | 1 | Artwork surround | Bedroom | CBM Millwork |  | 1 | assy | A11-09 | In Progress
2 | Artwork, Booth & Nightstands | 2 | Booth / banquette joinery |  | CBM Millwork |  | 1 | assy | A11-10 | In Progress
3 | Artwork, Booth & Nightstands | 3 | Nightstands (left & right) | Bedroom | CBM Millwork |  | 2 | pc | A2-01 | In Progress |  |  | Mocca Cafe tops via Stonework
4 | Bed | 1 | Bed base / platform joinery | Bedroom | CBM Millwork |  | 1 | assy | A11-08 | In Progress
5 | Cabinet Hardware | 1 | Drawer / rail runner | Vanity & millwork | Hafele | MATRIX runner BB A45 |  | set | A9-03 | In Progress |  |  | Named on vanity detail
6 | Cabinet Hardware | 2 | General cabinet hardware - hinges, slides, pulls, catches, soft-close | All millwork |  |  |  | lot | A11-05..10 | Not Started
7 | Closet Joinery | 1 ¦ D-03 | Walk-in closet joinery (louvered sliding doors, internal fit-out) | Closet | CBM Millwork |  | 1 | assy | A11-05 | In Progress |  |  | Stone tops via Stonework; door D-03 in Doors tracker
8 | Headboard | 1 | Headboard millwork | Bedroom | CBM Millwork |  | 1 | assy | A11-07A/B | In Progress
9 | Minibar | 1 | Minibar cabinetry (counter, back splash, integrated services) | Minibar | CBM Millwork |  | 1 | assy | A11-06A/B | In Progress |  |  | Red Soraya top via Stonework; socket cut-out open item 17

## 07 Plumbing Systems
07 Plumbing Systems
1 items · filter by Sub-Category to drill in
# | Sub-Category | Code / Tag | Item / Description | Location / Zone | Manufacturer / Brand | Model / SKU | Qty | Unit | Spec Ref | Spec Sheet | Approved | Procured | Notes
1 | Plumbing Specialties |  | Hose bib |  | PROFLO | PFXBVHBD | 2 |  | https://fergusonprod.a.bigcontent.io/v1/static/4631136_17452207_specification

## 08 Plumbing Equipment
08 Plumbing Equipment
5 items · filter by Sub-Category to drill in
# | Sub-Category | Code / Tag | Item / Description | Location / Zone | Manufacturer / Brand | Model / SKU | Qty | Unit | Spec Ref | Spec Sheet | Approved | Procured | Notes
1 | Domestic Water Piping & Valves |  | Ball Valves |  | Aquaram
2 | Domestic Water Piping & Valves | PVC elbows | Insulation |  |  | Micro-Lok
3 | Domestic Water Piping & Valves | PVC elbows | Cold water service |  |  | PVC SCH 40
4 | Domestic Water Piping & Valves | PVC elbows | Cold water distribution |  |  | CPVC
5 | Domestic Water Piping & Valves | PVC elbows | Hot water |  |  | CPVC

## 09 Pool & Water Features
09 Pool & Water Features
34 items · filter by Sub-Category to drill in
# | Sub-Category | Code / Tag | Item / Description | Location / Zone | Manufacturer / Brand | Model / SKU | Qty | Unit | Spec Ref | Spec Sheet | Approved | Procured | Notes
1 | Balancing Tank & Specialties | 1 ¦ F1 | Make-up float valve, 3/4 in NPT, brass | Balancing tank | Robert Mfg | BOB R400 3/4-5P-LF | 1 | no | https://www.cdivalve.com/images/uploads/Control_Devices_Float_Valve_Catalog.pdf | Complete |  |  | confirm vs Hayward request. RFI
2 | Balancing Tank & Specialties | 2 ¦ F2 | Foot valve, 2 in, PVC w/ strainer | Balancing tank | Spears | PVC | 1 | no | F2 | Complete
3 | Balancing Tank & Specialties | 3 ¦ F3 | Waterstop couplings (tank penetrations), fiberglass | Balancing tank | ASA | FPK-88-301.5/302/303/304 | 5 | no | F3 | Complete |  |  | CLARIF vs shell PVC sleeve. RFI
4 | Balancing Tank & Specialties | 4 ¦ F4 | Vent pipe, 1-1/2 in Sch 40 PVC | Balancing tank | Spears | Sch 40 PVC |  | run | F4 | Complete
5 | Balancing Tank & Specialties | 5 ¦ F5 | Overflow pipe, 4 in Sch 40 PVC (to soakaway) | Balancing tank | Spears | Sch 40 PVC | 2 | run | F4 | Complete |  |  | discharge verify on site. RFI
6 | Balancing Tank & Specialties | 6 ¦ F6 | Suction pipe to pump room, 2 in Sch 40 PVC | Balancing tank | Spears | Sch 40 PVC |  | run | F4 | Complete |  |  | ~80 ft
7 | Balancing Tank & Specialties | 7 ¦ F7 | Trough drain pipe, 2-1/2" in Sch 40 PVC | Balancing tank | Spears | Sch 40 PVC |  | run | F4 | Complete
8 | Filtration | 1 ¦ A1 | Cartridge filter, 150 sq ft, 15-5/8 in dia | Pump room | Pentair | Clean & Clear Plus CC150 (160317) | 1 | no | https://www.pentair.com/content/dam/extranet/nam/pentair-pool/residential/filters/filter-web-pages/support-pages/pentair-clean-and-clear-cartridge-filter-brochure-2025.pdf | Complete |  |  | SP-01 item 1. Status OK
9 | Pool Bonding & Electrical | 1 ¦ H1 | Equipotential bonding conductor, #8 AWG solid bare copper | Pool perimeter | - | #8 AWG bare copper |  | run | H1 | Complete |  |  | TBR - length per GP1-E3. NEC 680
10 | Pool Bonding & Electrical | 2 ¦ H2 | Bonding lugs / in-ground bond kit | Pool elements | Burndy | KA-series + BWB680IG kit |  | set | H2 | Complete |  |  | TBR - pump, heater, ladder, niches, main drain
11 | Pool Controls & Automation | 1 ¦ A5 | Pool controller | Pump room | Pentair | IntelliCenter Lite i5P (523911) | 1 | no | https://www.pentair.com/content/dam/extranet/nam/pentair-pool/residential/automation/intellicenter/manuals---user-docs/intellicenter-install-guide.pdf | Complete |  |  | 1 unit covers 2 pools. Status OK
12 | Pool Fittings | 1 ¦ B1 | Pool wall return inlet, 2 in | Pool | Hayward | SP1419GR (LIGHT GRAY) | 2 | no | https://static1.squarespace.com/static/6519e230af90b51759bda677/t/66cb857eb253041fc8392757/1724614014630/Hayward+Wall+Return+Fittings.pdf | Complete |  |  | Status OK; waterstop B9
13 | Pool Fittings | 2 ¦ B2 | Infinity edge return inlet, 2 in | Pool | Hayward | SP1419GR (LIGHT GRAY) | 6 | no | https://static1.squarespace.com/static/6519e230af90b51759bda677/t/66cb857eb253041fc8392757/1724614014630/Hayward+Wall+Return+Fittings.pdf | Complete |  |  | Status OK
14 | Pool Fittings | 3 ¦ B3 | Floor return inlet, 2 in (light gray, tile-match) | Pool floor | Color Match Pool Fittings | Pebble Top PTFR-03 (LIGHT GRAY TRIM) | 1 | no | https://static1.squarespace.com/static/55257138e4b0c26feadbc8ce/t/5b2bf42eaa4a999d8cfc8e9e/1529607217692/Pebble+Top+Floor+Return+Brochure+email.pdf | Complete |  |  | SUB - SP1425 not in gray. RFI 82 / SUB-248
15 | Pool Fittings | 4 ¦ B4 | Vacuum fitting, 2 in | Pool | Hayward | W400BLGP LIGHT GRAY | 1 | no | B4 | Complete |  |  | Status OK
16 | Pool Fittings | 5 ¦ B5 | Main drain 32 in X 8-1/2" | Pool floor | Pentair | AVSC LIGHT GRAY | 1 | kit | https://www.pentair.com/content/dam/extranet/nam/pentair-pool/residential/in-floor-cleaning-and-circulation/avsc-heavy-debris-removal/user-docs/avsc-drain-install-and-user-guide.pdf | Complete |  |  | sump+frame+2 covers. Status OK
17 | Pool Fittings | 6 ¦ B6 | Infinity edge trough drain outlet, 3 in | Trough | Spears | Sch 40 PVC 3 in | 8 | no | B5 | Complete |  |  | Status OK
18 | Pool Fittings | 7 ¦ B7 | Automatic water filler | Balancing tank | Pentair | T40-F | 1 | no | https://www.pentair.com/content/dam/extranet/nam/pentair-pool/residential/white-goods/auto-water-fillers/automatic-water-filler-brochure-english.pdf | Complete |  |  | SP-01 item 9. Status OK
19 | Pool Fittings | 8 ¦ B8 | Equalizer wall return inlet, 1-1/2 in | Pool | Hayward | SP1408 | 1 | no | B7 | Complete |  |  | auto-filler discharge
20 | Pool Fittings | 9 ¦ B9 | Waterstop sleeve fittings, PVC (2 in x11 + 1-1/2 in x1) | Pool shell | ASA | PVC Sleeve PVC-40-302 / 301 | 12 | no | B8 | Complete |  |  | CLARIF - drawing 'FPK-40-302' is a typo. RFI
21 | Pool Heating | 1 ¦ A6 | Pool heat pump, ~142k BTU, COP 6.2 | Equipment | Gulfstream | HE-150 (alt Pentair UltraTemp 140) | 1 | no | https://www.gulfstreamheatpump.com/models/#more-information | Complete |  |  | SUB from discontinued AquaCal SQ225. R3
22 | Pool Lighting | 1 ¦ D1 / L09 | Pool step submersible fixture, 12 W, 2 in | Pool steps | Pentair | IntelliVibe Micro 602280 | 8 | no | http://www.pentair.com/intellivibe | Complete |  |  | SUB from L&L Bright 1.6. R4. LD2-02 zone 3.8
23 | Pool Lighting | 2 ¦ D2 / L09.1 | Pool body submersible fixture, 12 W (Mezzo 24W alt) | Pool body | Pentair | IntelliVibe Micro (Mezzo 24W alt) | 5 | no | http://www.pentair.com/intellivibe | Complete |  |  | SUB from L&L Bright 3.0. R4
24 | Pool Lighting | 3 ¦ D3 | Light conduit, 2 in Sch 40 PVC | Pool | Spears | Sch 40 PVC | 13 | run | D2 | Complete |  |  | one run per fixture to driver/JB
25 | Pool Piping & Valves | 1 ¦ G1 | PVC ball valves | Pump room |  | PVC | 12 | no | G1 | Complete |  |  | TBR - qty per pump-room schematic (6-8 est)
26 | Pool Piping & Valves | 2 ¦ G2 | PVC check valves | Pump room |  | PVC | 4 | no | G2 | Complete |  |  | TBR (2 est)
27 | Pool Piping & Valves | 4 ¦ G4 | Balancing valves in enclosure | Pool |  | PVC | 9 | no | G4 | Complete |  |  | TBR - location & qty per design
28 | Pool Piping & Valves | 5 ¦ G5 | Main return pipe, 2 in Sch 40 PVC | Pump room to pool |  | Sch 40 PVC |  | run | G5 | Complete |  |  | Status OK
29 | Pool Piping & Valves | 6 ¦ G6 | Infinity edge main return, 2-1/2 in Sch 40 PVC | Pump room to edge |  | Sch 40 PVC |  | run | G5 | Complete |  |  | Status OK
30 | Pool Piping & Valves | 7 ¦ G7 | Fittings - elbows/tees/reducers/unions | - |  | Sch 40 PVC |  | lot | G5 | Complete |  |  | TBR - count from schematic
31 | Pool Piping & Valves | 8 ¦ G8 | Make-up water pipe, 3/4 in Sch 40 PVC | - |  | Sch 40 PVC |  | run | G5 | Complete |  |  | refer plumbing for continuation
32 | Pool Pumps | 1 ¦ A2 | Main filter pump, variable speed, 45 GPM @ 70 ft, 3 HP, 208-230V | Pump room | Pentair | IntelliFlo3 VSF | 1 | no | https://online.flippingbook.com/view/154564692/ | Complete |  |  | SP-01 item 2. Status OK
33 | Pool Pumps | 2 ¦ A3 | Infinity edge pump, variable speed, 90 GPM @ 50 ft, 3 HP | Pump room | Pentair | IntelliFlo3 VSF | 1 | no | https://online.flippingbook.com/view/154564692/ | Complete |  |  | SP-01 item 3. Status OK
34 | Sanitization & Chlorination | 1 ¦ A4 | Salt chlorine generator, power bundle | Pump room | Pentair | IntelliChlor LT25 (523750) | 1 | set | https://www.pentair.com/en-us/pool-spa/products/water-treatment/intellichlor-plus-lt-salt-chlorine-generators.html | Complete |  |  | SUB from AutoPilot DIG-220 (discontinued). R1

## 10 Electrical
10 Electrical
14 items · filter by Sub-Category to drill in
# | Sub-Category | Code / Tag | Item / Description | Location / Zone | Manufacturer / Brand | Model / SKU | Qty | Unit | Spec Ref | Spec Sheet | Approved | Procured | Notes
1 | Feeders, Cable, Conduit & Ground | 1 | Feeders, branch cabling, conduit, containment, earthing |  |  |  |  | lot | GP1-E4 | Not Started
2 | Feeders, Cable, Conduit & Ground | Cable | #2 AWG Cable Black (Copper) |  | N/A |  |  | FT | GP1R-E4
3 | Feeders, Cable, Conduit & Ground | Cable | #2 AWG Cable Red (Copper) |  | N/A |  |  | FT | GP1R-E4
4 | Feeders, Cable, Conduit & Ground | Cable | #2 AWG Cable White (Copper) |  | N/A |  |  | FT | GP1R-E4
5 | Feeders, Cable, Conduit & Ground | Cable | 3/0 AWG Cable Black (Copper) |  | N/A |  |  | FT | GP1R-E4
6 | Feeders, Cable, Conduit & Ground | Cable | 3/0 AWG Cable Red (Copper) |  | N/A |  |  | FT | GP1R-E4
7 | Feeders, Cable, Conduit & Ground | Cable | 3/0 AWG Cable White (Copper) |  | N/A |  |  | FT | GP1R-E4
8 | Feeders, Cable, Conduit & Ground | Cable | #6 AWG Cable Green (Copper) |  | N/A |  |  | FT | GP1R-E4
9 | Feeders, Cable, Conduit & Ground | Cable | #8 AWG Cable Green (Copper) |  | N/A |  |  | FT | GP1R-E4
10 | Panelboards & Distribution | 1 ¦ MGP1 | Main panelboard MGP1, 120/240V 1ph 3W, 225A bus, 175AT MB, 22kAIC, NEMA 3R | MEP module | Square D / Siemens or eq |  | 1 | no | GP1-E5 | In Progress |  |  | 44,065 VA connected / 184A
11 | Panelboards & Distribution | 2 ¦ GP1 | Sub-panel GP1, 150A bus, 80AT MB, 22kAIC, NEMA 1/2 | Guest Pavilion | Square D / Siemens or eq |  | 1 | no | GP1-E5 | In Progress |  |  | 10,803 VA / 45A
12 | Panelboards & Distribution | 3 | 225A Meter Combo, 175A MCB, NEMA 3R, 120/240V, 1PH, 3W
13 | Panelboards & Distribution | 4 ¦ GP1 | SPD, 160KA Surge Current Rating, Multimode Protection, 80KA Per Mode, Service Entrance MCOV= 140V To 150V RMS Voltage Nominal= 240/120V, 1PH, 3W, UL Listed, Side Mounted, NEMA 3R | MEP Module |  |  | 1 | no | GP1-E5
14 | Wiring Devices & Power | 1 | Wiring devices - switches, outlets, cover plates (general) | Guestroom |  |  |  | lot | GP1-E2 | Not Started |  |  | Lutron receptacles/faceplates tracked in Lighting (LTG-04)

## 11 Low Voltage & ICT
11 Low Voltage & ICT
1 items · filter by Sub-Category to drill in
# | Sub-Category | Code / Tag | Item / Description | Location / Zone | Manufacturer / Brand | Model / SKU | Qty | Unit | Spec Ref | Spec Sheet | Approved | Procured | Notes
1 | Telephone, CATV, IT & Data | 1 | Structured cabling / outlets / risers - telephone, CATV, IT / data | Guestroom |  |  |  | lot | GP1-E6 | Not Started

## 12 Lighting
12 Lighting
42 items · filter by Sub-Category to drill in
# | Sub-Category | Code / Tag | Item / Description | Location / Zone | Manufacturer / Brand | Model / SKU | Qty | Unit | Spec Ref | Spec Sheet | Approved | Procured | Notes
1 | Architectural Luminaires | 1 ¦ L01 | Recessed downlight, 14 deg | Interior ceilings |  |  | 13 | pc | Luminaire Sched | In Progress
2 | Architectural Luminaires | 2 ¦ L02 | Recessed downlight, 26 deg | Interior ceilings |  |  | 12 | pc | Luminaire Sched | In Progress
3 | Architectural Luminaires | 3 ¦ L02.1 | Recessed projector, 24 deg (accent) | Interior ceilings |  |  | 4 | pc | Luminaire Sched | In Progress
4 | Architectural Luminaires | 4 ¦ L07 | Wall niche / step light | Stair / niche |  |  | 4 | pc | Luminaire Sched | In Progress
5 | Architectural Luminaires | 5 ¦ L06.1 | Integrated mini-downlight (closet/vanity/minibar) | Furniture |  |  | 16 | pc | Luminaire Sched | In Progress
6 | Architectural Luminaires | 6 ¦ L12 | Surface-mounted service downlight | Service / BOH |  |  | 1 | pc | Luminaire Sched | In Progress
7 | Decorative Fixtures | 1 ¦ D01 | Sconce (Ella OUT 1.0) | Exterior wall |  | Ella OUT 1.0 | 1 | pc | Luminaire Sched | In Progress
8 | Decorative Fixtures | 2 ¦ D01.2 | Sconce + reading light | Bedroom (reading) |  |  | 2 | pc | Luminaire Sched | In Progress
9 | Decorative Fixtures | 3 ¦ D01.3 | Indirect wall lamp (Foil) | Interior wall |  | Foil | 2 | pc | Luminaire Sched | In Progress
10 | Decorative Fixtures | 4 ¦ D02 | Table lamp (Una Small) | Minibar |  | Una Small | 1 | pc | Luminaire Sched | In Progress
11 | Decorative Fixtures | 5 ¦ D03 | Floor lamp (Kando P/111) | Pool terrace |  | Kando P/111 | 1 | pc | Luminaire Sched | In Progress
12 | Decorative Fixtures | 6 ¦ P01 | Portable lamp (Kando M/40/R) | Portable |  | Kando M/40/R | 1 | pc | Luminaire Sched | In Progress
13 | LED Strips & Drivers | 1 ¦ L03 | Indirect LED strip (cove) | Living / outdoor living |  |  | 26 | ft | Luminaire Sched | In Progress
14 | LED Strips & Drivers | 2 ¦ L05.1 | LED strip in furniture, 2.93 W/ft | Bedroom (headboard) |  |  | 18.17 | ft | Luminaire Sched | In Progress
15 | LED Strips & Drivers | 3 ¦ L05.2 | LED strip in furniture, 0.73 W/ft | Bedroom (under bed) |  |  | 8 | ft | Luminaire Sched | In Progress
16 | LED Strips & Drivers | 4 ¦ L05.4 | LED strip in furniture, IP67 | Bathroom (wet) |  |  | 1 | ft | Luminaire Sched | In Progress
17 | LED Strips & Drivers | 5 ¦ L07.2 | LED strip in exterior step | Exterior steps |  |  | 1.58 | ft | Luminaire Sched | In Progress
18 | Lighting Control System (Lutron) | 1 | myRoom XC guestroom processor, DIN-rail | MEP | Lutron | MP-1L-GCU | 1 | pc | Report Pkg Rev5 | Complete |  |  | lights/shades/temp + PMS/BMS
19 | Lighting Control System (Lutron) | 10 | International-style wallbox / back box | Guestroom | Lutron | EBB-1-SQ | 10 | pc | Report Pkg Rev5 | Complete |  |  | DISCREPANCY: confirm vs EBB-15-SQ
20 | Lighting Control System (Lutron) | 11 | Radio Powr Savr wireless ceiling occupancy sensor | Guestroom | Lutron | LRF2-OCR2B-P-WH | 4 | pc | Report Pkg Rev5 | Complete
21 | Lighting Control System (Lutron) | 12 | Wireless QS sensor module, 434 MHz, ceiling | Guestroom | Lutron | QSM2-XW-C | 1 | pc | Report Pkg Rev5 | Complete |  |  | DISCREPANCY: 434MHz part is QSM2-4W-C
22 | Lighting Control System (Lutron) | 13 | Maestro PIR occupancy/vacancy switch, 2A | Guestroom | Lutron | MS-OPS2-WH | 1 | pc | Report Pkg Rev5 | Complete
23 | Lighting Control System (Lutron) | 14 | Claro 1-gang faceplate, white | Guestroom | Lutron | CW-1-WH | 1 | pc | Report Pkg Rev5 | Complete
24 | Lighting Control System (Lutron) | 15 | myRoom Palladiom thermostat w/ occ + humidity | Guestroom | Lutron | MWP-T-OHW-WH-A | 1 | pc | Report Pkg Rev5 | Complete |  |  | DISCREPANCY: finish -CP-A vs -WH-A
25 | Lighting Control System (Lutron) | 16 | Palladiom fan-coil controller | Guestroom | Lutron | SMC55-MYRM | 1 | pc | Report Pkg Rev5 | Complete |  |  | HVAC valve/fan control
26 | Lighting Control System (Lutron) | 17 | QS contact-closure interface, 5 in / 5 relay | MEP | Lutron | QSE-IO | 1 | pc | Report Pkg Rev5 | Complete
27 | Lighting Control System (Lutron) | 18 | 8-yr limited parts warranty + 2-yr diagnostic labor | - | Lutron | LSC-L2-P8LTD | 1 | ls | Quote Rev14 | Complete |  |  | service line
28 | Lighting Control System (Lutron) | 19 | Palladiom USB C-C receptacle, matte black (ADD Rev14) | Guestroom | Lutron | LTR-15-CCTR-BL | 5 | pc | Quote Rev14 | In Progress |  |  | ADDED Rev14 - not in drawings; verify
29 | Lighting Control System (Lutron) | 2 | myRoom QS-link DIN power supply, 120-240V, 30 PDU | MEP | Lutron | MQSPS-DH-1-30 | 1 | pc | Report Pkg Rev5 | Complete
30 | Lighting Control System (Lutron) | 20 | New Architectural duplex 15A TR receptacle, black (ADD) | Guestroom | Lutron | LTR-15-TR-BL | 7 | pc | Quote Rev14 | In Progress |  |  | ADDED Rev14 - verify
31 | Lighting Control System (Lutron) | 21 | Palladiom 1-gang faceplate, satin brass (ADD) | Guestroom | Lutron | LWT-U-P-SB | 12 | pc | Quote Rev14 | In Progress |  |  | ADDED Rev14 - verify
32 | Lighting Control System (Lutron) | 22 | Nova T 15A GFCI self-test TR, black (ADD) | Guestroom | Lutron | NTR-15-GFST-BL | 3 | pc | Quote Rev14 | In Progress |  |  | ADDED Rev14 - verify
33 | Lighting Control System (Lutron) | 23 | Architectural 1-gang plate, satin brass (ADD) | Guestroom | Lutron | NT-R3-NFB-SB | 3 | pc | Quote Rev14 | In Progress |  |  | ADDED Rev14 - desc contradictory
34 | Lighting Control System (Lutron) | 24 | Grafik Eye Class-2 LV cable, 5-cond, 500 ft (ADD) | - | Lutron | GRX-CBL-46L-500 | 1 | spool | Quote Rev14 | In Progress |  |  | ADDED Rev14
35 | Lighting Control System (Lutron) | 25 | Factory commissioning by Lutron Engineering (ADD) | - | Lutron | Factory Commissioning | 1 | ls | Quote Rev14 | In Progress |  |  | service line
36 | Lighting Control System (Lutron) | 3 | HWQS feed-through DIN rough-in panel | MEP | Lutron | PD4-36F-120 | 1 | pc | Report Pkg Rev5 | Complete
37 | Lighting Control System (Lutron) | 4 | 4-zone adaptive phase-dim power module, 1A | MEP | Lutron | MQSE-4A1-D | 2 | pc | Report Pkg Rev5 | Complete
38 | Lighting Control System (Lutron) | 5 | 2-zone switching power module, 1A | MEP | Lutron | MQSE-2S1-D | 1 | pc | Report Pkg Rev5 | Complete
39 | Lighting Control System (Lutron) | 6 | Energi Savr Node universal DALI, 1 loop | MEP | Lutron | QSN-1DALUNV-D | 1 | pc | Report Pkg Rev5 | Complete |  |  | DISCREPANCY: Rev14 lists QSN2-1DALUNV-D
40 | Lighting Control System (Lutron) | 7 | Alisse 1-column keypad, custom color | Guestroom | Lutron | HW-NW-KP-S1-E | 7 | pc | Report Pkg Rev5 | Complete
41 | Lighting Control System (Lutron) | 8 | Alisse 2-column keypad, custom color | Guestroom | Lutron | HW-NW-KP-S2-E | 3 | pc | Report Pkg Rev5 | Complete
42 | Lighting Control System (Lutron) | 9 | Alisse QS keypad mounting base | Guestroom | Lutron | HW-QS-B-S1 | 10 | pc | Report Pkg Rev5 | Complete

## 13 HVAC & Mechanical
13 HVAC & Mechanical
17 items · filter by Sub-Category to drill in
# | Sub-Category | Code / Tag | Item / Description | Location / Zone | Manufacturer / Brand | Model / SKU | Qty | Unit | Spec Ref | Spec Sheet | Approved | Procured | Notes
1 | Air Distribution | HVC-03 ¦ S/R | Supply air grille, opposed blade damper | Ceiling | Titus | 272FL | 0 | pc | GP1-AC-01 | Not Started | Not Started | Not Started | Supply grille (S/R, Titus 272FL). 0 on GP1 mock-up plan — AC-01 schedule type not used in this room (full AC-1 plan checked).
2 | Air Distribution | HVC-03 ¦ R/R | Return air grille, opposed blade damper | Ceiling | Titus | 272FL | 0 | pc | GP1-AC-01 | Not Started | Not Started | Not Started | Return grille (R/R, Titus 272FL). 0 on GP1 mock-up plan — AC-01 schedule type not used in this room (full AC-1 plan checked).
3 | Air Distribution | HVC-03 ¦ S/R1 | Supply linear bar diffuser, border Type 11, 0° deflection, AG-35-AA OBD | Ceiling | Titus | CT-540 | 0 | pc | GP1-AC-01 | Not Started | Not Started | Not Started | Supply CT-540 (S/R1). 0 on GP1 mock-up plan — AC-01 schedule type not used in this room (full AC-1 plan checked). On AC-1 the CT-540 devices are returns (R/R1) - see R/R1 row.
4 | Air Distribution | HVC-03 ¦ S/R2 | Supply linear bar diffuser, Type 11, 15° deflection, OBD | Ceiling | Titus | CT-541 | 1 | pc | GP1-AC-01 | Not Started | Not Started | Not Started | Confirmed on AC-1: S/R2 12x4, 120 CFM x1.
5 | Air Distribution | HVC-03 ¦ C/D | Aluminium supply ceiling diffuser, OBD | Ceiling | Titus | TDC-AA | 0 | pc | GP1-AC-01 | Not Started | Not Started | Not Started | Ceiling diffuser (C/D, TDC-AA). 0 on GP1 mock-up plan — AC-01 schedule type not used in this room (full AC-1 plan checked).
6 | Air Distribution | HVC-03 ¦ C/R | Aluminium return diffuser, double deflection | Ceiling | Titus | 55FL | 0 | pc | GP1-AC-01 | Not Started | Not Started | Not Started | Return diffuser (C/R, 55FL). 0 on GP1 mock-up plan — AC-01 schedule type not used in this room (full AC-1 plan checked).
7 | Air Distribution | HVC-03 ¦ EAG | Exhaust air grille, 45° fixed deflection, OBD | Ceiling | Titus | 3FL | 0 | pc | GP1-AC-01 | Not Started | Not Started | Not Started | Exhaust grille (EAG, 3FL). 0 on GP1 mock-up plan — AC-01 schedule type not used in this room (full AC-1 plan checked). Exhaust in WC/shower is via EF-GP1R-1/2 integral grilles.
8 | Air Distribution | HVC-03 ¦ FL-10-JT(S) | Linear flow bar (jet-throw) w/ pattern controller, 24" pre-insulated plenum box & butterfly damper | Ceiling | Titus | FL-10-JT | 4 | pc | GP1-AC-01 | Not Started | Not Started | Not Started | Confirmed on AC-1: 4x FL-10-JT(S) - 150 CFM (2'L/8"o), 340 CFM (4'L/10"o), 340 CFM (4'L/10"o), 145 CFM (2'L/8"o). Tracker said 'FL-series'; schedule also lists high-throw FL-XX-HT variant.
9 | Air Distribution | HVC-03 ¦ R/R1 | Return linear bar diffuser, Type 11, 0° deflection, AG-35-AA OBD | Ceiling | Titus | CT-540 | 2 | pc | GP1-AC-01 | Not Started | Not Started | Not Started | ADDED per AC-01 schedule + AC-1 plan: R/R1 returns 24x16 (830 CFM) & 12x8 (265 CFM). Missing from original tracker. ¦ Added during drawing review
10 | Air Distribution | HVC-03 ¦ R/R2 | Return linear bar diffuser, Type 11, 15° deflection, OBD | Ceiling | Titus | CT-541 | 0 | pc | GP1-AC-01 | Not Started | Not Started | Not Started | Return CT-541 (R/R2), counterpart to S/R2. 0 on GP1 mock-up plan — AC-01 schedule type not used in this room (full AC-1 plan checked). ¦ Added during drawing review
11 | Condensing Units | HVC-02 ¦ CU-GP1R | Outdoor condensing unit, R410A, 208-230/1/60, 20.2 FLA | Outdoor (on concrete pad) | Mitsubishi Electric | MXZ-SM36NAM2-U1 | 1 | no | GP1-AC-01 | Not Started | Not Started | Not Started | Confirmed AC-01. MOCP 40 A, 271 lb, 42x14x53", ambient 95/83°F. Neoprene isolator + SS anchors on concrete pad; factory seacoast protection, no on-site coating (AC-01 notes 2-3). Refrig lines 5/8" suc / 3/8" liq. Dwg tag = CU-GP1R (tracker had CU-GP1).
12 | Controls / Thermostats | HVC-07 ¦ LTG-04 | Room controllers / thermostats + control wiring | Guestroom | Lutron | SMC55-MYRM (Lutron FCU Controller) | 1 | lot | GP1-AC-01 | Not Started | Not Started | Not Started | AC-01 CU schematic shows Mitsubishi PAR-series controller (e.g. PAR-CT01MAU-SB) as OEM option; project direction is Lutron (LTG-04). Lutron FCU controller SMC55-MYRM + Palladiom thermostat - confirm exact t-stat model via Lutron quote. 1 thermostat shown on AC-1. ¦ Lutron Palladiom thermostat/FCU controller tracked in Lighting (LTG-04) - coordinate
13 | Ductwork, Dampers & Insulation | HVC-05 ¦ — | Ductwork, volume & fire dampers, duct insulation | Guestroom | — | — | 1 | lot | GP1-AC-02/03 | Not Started | Not Started | Not Started | Sizes per AC-1: 18x12 supply to roof; 24x16 & 12x8 returns; 8x8/8x6/6x6/6x4 branches; 6x4 exhaust to roof cap. Details AC-02/03: turning vanes, volume/splitter/balancing dampers, flex-duct support, strap hangers.
14 | Indoor Units (Fan Coils) | HVC-01 ¦ FCU-GP1R | Ducted split-system indoor fan-coil unit, vertical ducted, 36,000 BTU/hr (3.0 tons), R410A | Guest Pavilion 1 (Mock-Up Room) | Mitsubishi Electric | PVFY-P36NAMU-E1 | 1 | no | GP1-AC-01 | Not Started | Not Started | Not Started | Confirmed on AC-01 Split-System schedule & AC-2 section. Supply air 767/931/1,095 CFM (3-spd), ESP 0.8" WG, sensible 26,300 BTU/hr, 141 lb, 22x21x55". Dwg tag = FCU-GP1R (tracker had FCU-GP1).
15 | Refrigerant Piping | HVC-06 ¦ — | Insulated refrigerant copper piping & accessories | FCU-GP1R to CU-GP1R | — | — | 1 | lot | GP1-AC-01/02 | Not Started | Not Started | Not Started | Line sizes per AC-01: 5/8" suction / 3/8" liquid, R410A. Underground runs in PVC sleeves (AC-1 note). Supports per AC-03 details.
16 | Ventilation / Exhaust Fans | HVC-04 ¦ EF-GP1R-1 | Ducted centrifugal exhaust fan, 70 CFM, 0.1" W.G. | WC (GP1) | Panasonic | RG-M79LA | 1 | no | GP1-AC-01 | Not Started | Not Started | Not Started | Confirmed AC-01 Exhaust Fan schedule + AC-1. Static pressure 0.1" W.G. - tracker '0.8 in ESP' appears to be an error (0.8 is the FCU ESP). 18.5 W, 995 RPM, 120/1/60, ceiling, 6x4 duct to roof cap. Dwg tag EF-GP1R-1.
17 | Ventilation / Exhaust Fans | HVC-04 ¦ EF-GP1R-2 | Ducted centrifugal exhaust fan, 70 CFM, 0.1" W.G. | Shower (GP1) | Panasonic | RG-M79LA | 1 | no | GP1-AC-01 | Not Started | Not Started | Not Started | Confirmed AC-01 + AC-1. Same spec as EF-GP1R-1. Dwg tag EF-GP1R-2.